## Dashboard
CONSTRUCTION PROJECT BUDGET DASHBOARD
Generated by Flowtech Advisory ¦ Update figures monthly
Project Name | Budget ($) | Actual ($) | Variance ($) | Variance % | % Complete | Status
Riverside Tower - Stage 1 | 4500000 | 4200000 |  |  | 85%
Metro Station Upgrade | 12000000 | 13500000 |  |  | 62%
Harbour Bridge Maintenance | 2800000 | 2650000 |  |  | 95%
CBD Office Fit-out L12 | 1200000 | 1180000 |  |  | 78%
Westfield Expansion Wing C | 8500000 | 7900000 |  |  | 45%
TOTAL

## Cost Breakdown
COST BREAKDOWN BY CATEGORY
Category | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
BUDGET
Labour | 380000 | 395000 | 410000 | 420000 | 415000 | 400000 | 390000 | 410000 | 425000 | 430000 | 420000 | 380000
Materials | 250000 | 280000 | 320000 | 350000 | 340000 | 310000 | 290000 | 330000 | 360000 | 340000 | 300000 | 260000
Equipment | 120000 | 125000 | 130000 | 135000 | 130000 | 125000 | 120000 | 130000 | 135000 | 130000 | 125000 | 120000
Subcontractors | 450000 | 480000 | 520000 | 550000 | 540000 | 500000 | 470000 | 530000 | 560000 | 540000 | 490000 | 440000
Overheads | 85000 | 85000 | 90000 | 90000 | 90000 | 85000 | 85000 | 90000 | 90000 | 90000 | 85000 | 85000
Contingency | 50000 | 50000 | 55000 | 55000 | 55000 | 50000 | 50000 | 55000 | 55000 | 55000 | 50000 | 50000
BUDGET TOTAL
ACTUAL
Labour | 390000 | 405000 | 425000 | 440000 | 430000 | 415000 | 400000 | 0 | 0 | 0 | 0 | 0
Materials | 260000 | 295000 | 340000 | 370000 | 355000 | 325000 | 300000 | 0 | 0 | 0 | 0 | 0
Equipment | 125000 | 130000 | 140000 | 145000 | 138000 | 132000 | 128000 | 0 | 0 | 0 | 0 | 0
Subcontractors | 460000 | 500000 | 545000 | 580000 | 560000 | 520000 | 490000 | 0 | 0 | 0 | 0 | 0
Overheads | 88000 | 92000 | 95000 | 93000 | 91000 | 88000 | 87000 | 0 | 0 | 0 | 0 | 0
Contingency | 15000 | 25000 | 30000 | 40000 | 20000 | 10000 | 5000 | 0 | 0 | 0 | 0 | 0
ACTUAL TOTAL
VARIANCE (Budget - Actual)
VARIANCE

## Instructions
CONSTRUCTION BUDGET DASHBOARD - INSTRUCTIONS
How to Use This Dashboard
1. Dashboard Tab
- Enter your project names in column A (rows 5-9)
- Enter the total budget for each project in column B
- Enter the actual spend to date in column C
- Variance and Status columns calculate automatically
- Update the % Complete column manually each month
- Charts update automatically when data changes
2. Cost Breakdown Tab
- Budget section: Enter your planned monthly spend per category
- Actual section: Enter actual monthly spend as invoices are processed
- Variance section calculates automatically
- Green = under budget, Red = over budget
3. Adding More Projects
- Insert rows above the TOTAL row on the Dashboard tab
- Copy formulas from an existing row
- Update the chart data range to include new rows
4. Formula Reference
- Variance = Budget - Actual
- Variance % = Variance / Budget
- Status = IF(Variance >= 0, "Under Budget", "Over Budget")
- All totals use SUM formulas
5. Tips
- Print the Dashboard tab for monthly project meetings
- Use the Cost Breakdown for detailed financial reviews
- Back up this file monthly before making changes
- Protect sheets (Review > Protect Sheet) to prevent accidental edits