## Daily Runsheet
DAILY SITE RUNSHEET
Project Name: |  |  |  | Site Address:
Date: |  |  |  | Weather:
Site Manager: |  |  |  | Shift:
SECTION 1: PERSONNEL ON-SITE
Name | Company | Role | Trade | Start | Finish | Hours | Notes
Total Personnel: |  |  |  | Total Hours:
SECTION 2: PLANT & EQUIPMENT
Item/Description | Supplier | Docket No. | Hours Used | Status | Operator | Location | Notes
SECTION 3: WORK COMPLETED TODAY
Area / Zone | Description of Work |  | Trade | % Complete | Planned % | Variance | Notes
SECTION 4: SAFETY OBSERVATIONS
Time | Observation |  | Risk Level | Action Required |  | Responsible | Closed?
SECTION 5: DELAYS / ISSUES
Description |  | Impact (hrs) | Cause | Action Taken |  | Responsible | Resolved?
SECTION 6: MATERIALS DELIVERED
Item | Quantity | Unit | Supplier | Docket No. | Received By | Storage Location | Condition
Prepared By: |  |  |  | Date:
Signature: |  |  |  | Reviewed By:

## Instructions
SITE DAILY RUNSHEET - INSTRUCTIONS
Purpose
This template captures daily site activities for construction projects.
Complete it at the end of each day and submit to the Project Manager.
Section Guide
Section 1: Personnel On-Site
Record all personnel present on site including subcontractors and visitors.
Start/Finish times should be in 24-hour format (e.g., 07:00, 15:30).
Hours column should show total hours worked (excluding breaks).
Section 2: Plant & Equipment
List all plant and equipment used on site that day.
Status options: In Use, Idle, Breakdown, Maintenance.
Record docket numbers for hired equipment.
Section 3: Work Completed Today
Describe work by area/zone for easy tracking against the programme.
% Complete should reflect cumulative progress, not just today's work.
Variance auto-calculates (Actual % minus Planned %).
Section 4: Safety Observations
Record all safety observations, near-misses, and positive observations.
Risk Level: Low, Medium, High, Critical.
All observations must have an action and responsible person.
Section 5: Delays / Issues
Document any delays or issues affecting the programme.
Quantify the impact in hours where possible.
Include weather delays, material shortages, coordination issues.
Section 6: Materials Delivered
Record all material deliveries with docket numbers.
Note condition on arrival (Good, Damaged, Incomplete).
Tips for Daily Use
- Fill in the header info (project, date, weather) first thing each morning
- Update personnel as they sign in/out throughout the day
- Note safety observations as they happen, not at end of day
- Take photos to support any observations or issues noted
- Submit by 6:00 PM each day to the Project Manager
- Keep a copy for site records